## Bug_Tracker
Bug ID | Date Reported | Module | Feature | Reported By | Assigned To | Severity | Priority | Status | Environment | Summary | Steps to Reproduce | Expected Result | Actual Result | Attachment | Resolution | Closed Date
BUG-001 | 2026-08-01 | Authentication | Login | Rishabh | Backend Developer | High | P1 | Open | Windows 11 ¦ FastAPI ¦ PostgreSQL | Login API returns HTTP 500 for invalid credentials | 1. Open Swagger 2. POST /auth/login 3. Enter wrong password 4. Execute | 401 Unauthorized | 500 Internal Server Error | Screenshot
BUG-002 | 2026-08-01 | Complaint | Image Upload | Rishabh | Backend Developer | Medium | P2 | Open | Windows 11 ¦ FastAPI ¦ PostgreSQL | Unsupported file type accepted | Upload .txt file as complaint image | Validation error shown | Upload succeeds | Screenshot
BUG-003 | 2026-08-01 | Analytics | Dashboard | Rishabh | Frontend Developer | Low | P3 | In Progress | Chrome ¦ React | Complaint count not refreshed | Resolve complaint then open dashboard | Dashboard auto-refreshes | Manual refresh required | Screenshot